## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Blue Group
| Project | Airline Reservation System
| Product Owner | Wayne & Ashton
| Scrum Master | Ashton & Wayne
| Development Team | Wayne & Ashton
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Search Flight Availability | As a traveler, I want to search for available flights so that I can find travel options that meet my needs. | User can input origin, destination, date and receive results | 1 | 1 | Developer
2 | Retrieve Flight Data | System retrieves available flight data from airline sources | System successfully retrieves flight data from source | 2 | 1 | Developer
3 | Store Flight Data | Store flight data in a database | Flight data is saved and can be accessed later | 3 | 1 | Developer
4 | Display Flight Results | Present users with available flights | Users can view a list of matching flights | 4 | 1 | Developer
5 | Select Flight | As a user, I want to select a flight from the available options so that I can proceed with booking. | User can select a flight from results | 5 | 2 | Developer
6 | Enter Passenger Information | Collect user personal details | User can enter required booking information | 6 | 2 | Developer
7 | Validate Passenger Information | Ensure entered data is correct | System prevents invalid or missing data submission | 7 | 2 | Developer
8 | Process Payment | As a customer, I want to securely pay for my flight so that I can complete my booking. | User can submit payment and complete purchase | 8 | 2 | Developer
9 | Validate Payment Information | Ensure payment data is valid | Invalid payment details are rejected | 9 | 3 | Developer
10 | Confirm Booking | Provide confirmation after booking | User receives confirmation of successful booking | 10 | 3 | Developer
11 | Generate Booking Record | Store booking in system | Booking is saved with unique identifier | 11 | 3 | Developer
12 | User Registration | As a new user, I want to create an account so that I can manage my bookings. | User can successfully create account | 12 | 3 | Developer
13 | User Login | Allow users to log in | User can log in with valid credentials | 13 | 3 | Developer
14 | Manage User Accounts | Allow users to update profile | User can modify account information | 14 | 4 | Developer
15 | Store Customer Data | Maintain customer account data | Customer data is stored securely | 15 | 4 | Developer
16 | View Booking History | Allow users to view past bookings | User can see previous reservations | 16 | 4 | Developer
17 | Track Flight Status | As a user, I want to track my flight status so that I can stay informed of any changes. | User can view current flight status | 17 | 4 | Developer
18 | Flight Status Updates | Provide updates (delay/cancel) | System reflects updated flight status | 18 | 5 | Developer
19 | Notification System | Notify users of updates | User receives booking and status notifications | 19 | 5 | Developer
20 | Error Handling and Validation | Handle system errors gracefully | System does not crash on invalid input | 20 | 6 | Developer
21 | Security and Data Protection | Protect sensitive user data | User data is protected and access is restricted to authorized users | 21 | 7 | Developer
22 | User Interface (UI) System | Provide user-friendly interface | Interface allows easy navigation and interaction | 22 | 7 | Developer
23 | Session Management | Maintain user sessions | User session persists during use | 23 | 6 | Developer
24 | Logout Functionality | Allow users to log out | User can securely log out of system | 24 | 6 | Developer
25 | Admin/Reporting Features | Track system data for business use | System can display booking and sales data | 25 | 7 | Developer

## Sprint 0
Sprint #0Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 0
|  | Start date |  | 2026-03-30
|  |  | Total Team Members | 2
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05
|  | Create initial product backlog | Developer 1 | 3 |  | 3
|  | Define project scope and requirements | Developer 2 | 2 |  |  | 1 | 1
|  | Identify MVP features | Developer 1 | 2 |  | 1 |  | 1
|  | Design high-level system architecture | Developer 2 | 3 |  |  | 1 | 1 | 1
|  | Plan sprint breakdown (assign stories to sprints) | Both | 3 |  |  | 1 | 1 | 1
|  | Review and finalize backlog | Both | 2 |  |  |  |  | 1 | 1
|  | Remaining units (actual) |  | 20 | #N/A | 16 | #N/A | 9 | 6 | 5 | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 15 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 1
Start date
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 2
Start date
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 3
Sprint #3Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 3
Start date
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 4
Sprint #4Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 4
|  | Start date |  | 2025-05-13
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 5
Sprint #5Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 5
|  | Start date |  | 2025-05-13
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 6
Sprint #6Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 6
|  | Start date |  | 2025-05-13
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0

## Sprint 7
Sprint #7Tracking Sheet
|  | Project |  | Airline Reservation System
|  | Sprint # |  | 7
Start date
|  |  | Total Team Members | 3
week 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
|  | Remaining units (actual) |  | 30 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 10 | 0 | 10 | 0